## Sheet1
KEY
	Urgent
	In-progress
	Pending
	Done
	Title
	Performed Weekly
Are: Augmented Reality Education	October					November				December – Assessment
Week Commercing	1	2	3	4	5	6	7	8	9	10	11	12	13
WEEK
PRE-PRODUCTION
Research other AR apps for education
Sketch storyboard
Animatics – Video playout of Storyboard
Research Mathematics topic for AR experience
PRODUCTION
Model Asset – Building
Blender – Tripod
Blender – Grass
Blender – Trees
Blender – Ground/Earth
Blender – Character – Surveyor
Blender – Heart model modification and inner section creation
Blender – LightStand
Unity & Vuforia – Create Basic AR system
Vuforia – Create test marker
Vuforia – Create marker database
Unity – Create test controls: Translate
Unity – Create test controls: Rotate
Unity – Create test controls: Scale
Uv Unwrap Asset
Texture Assets
Texture – Tripod
Texture – Grass
Texture – Trees
Texture – Ground/Earth
Texture – Character – Surveyor
Texture – LightStand
Animate Assets
Animate – Surveyor
Animate – Trees
Animate – Heartbeat
LABELS & ANNOTATION
Create mathematics lables and information
Create heart section labels
UNITY AR DEVELOPMENT
Create interaction controls – Touch and hold (Hide/show detailed labels and information)
Create interaction controls – Double tap screen (Hide/show quick labels and model sections)
Design Final Apk math marker
Design Final Apk heart marker
Vuforia – create new marker database
Unity – integrate new marker
USER TESTING
UT – Feature & Functionality test
Unity – integrate new marker
WRAP UP EXPERIENCE
Research – Reading
Finish for assessment
Final changes for degree show
WRITTEN ASSESSMENT
Introduction
Lit review
Main essay
Professional Practice Portfolio