## Sheet1
KEY
urgent
in process
done
FMP PROJECT
Week commencing | OCTOBER |  |  |  |  | NOVEMBER |  |  |  | DECEMBER - ASSESSMENT | SHOWCASE
WEEK | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
PRE-PRODUCTION
Research and idea development
Call out for primary source material
Finalise script
Call out for actors |  |  |  | emailed amanda | put out poster
Book central loans - for audio narration (book room and zoom H5)
Book central loans - for volumetric capture (book portable green screen, lighting and tripod)
Run gofundme campaign
USER TESTING 1
Assess reaction and feelings towards current written up experiences
PRODUCTION
Record narration
Edit audio
Storyboard for volumetric capture based on audio
Record volumetric capture (ensuring it fits audio)
Edit volumetric capture - after effects double depth input
POST-PRODUCTION
Unity - create main scene: seated experience
Tilt brush - title scene, trigger warnings, credits and any other written elements
Unity - add volumetric capture and audio (attached to each other)
Unity - how do I get the scenes to play out correctly?
Gaze activation or any other interactive elements?
Extra visuals - skybox created in AE or PARTICLES
USER TESTING 2
Gauge reaction and feelings towards narrative with visuals and audio - Feedback
Implement changes from feedback
WRAPAROUND EXPERIENCE
Research
Gathering resources
Curating
User test and make changes
Finish for assessment
Final changes for degree show
WRITTEN ASSESSMENTS
Lit review
Define research questions
Write essay
Professional Practic Portfolio